CERTUS

18-WEEK WORK PLAN

Solo Execution Companion to the Technical Blueprint

| Owner | Rishikesh Talpaliker — Solo Developer |
| --- | --- |
| Team Configuration | Solo (single-owner execution across all roles) |
| Window | 18 calendar weeks, 10 Aug – 13 Dec 2026 |
| Companion Document | Certus — Technical Blueprint (v1.0) |
| Version | v1.0 |
| Date | 15 August 2026 |

How to use this document

One card per week. Six weeks are milestone/gate weeks (2, 5, 8, 10, 12, 16), marked in amber,

with a heavier gate-review bar than an ordinary week.

WEEK 1 — Data Audit & Literature

This Week's Work - Inventory every image in the CBRI dataset: total count, defect-positive count, per-class breakdown. - Determine whether site_id and camera_id metadata exists; if not, plan proxy derivation from EXIF, filenames, or feature clustering. - Read Angelopoulos & Bates, "A Gentle Introduction to Conformal Prediction," end to end — the full tutorial, appendices included. - Set up the repo skeleton, DVC, Weights & Biases, pre-commit hooks, and CI. - Write the three contribution claims into paper/intro.tex, verbatim, and lock them. Weekly Deliverable n_pos counted and written down; repo initialised with its first real commit on main. Review Evidence / Logbook Entry Logbook entry with the exact n_pos figure and the achievable ε range it implies; repo visible on GitHub with CI passing.

WEEK 2 — Shift Verification & Scope Lock MILESTONE / GATE — Hard gate — 400+ defect-positive images across 3+ distinguishable sites, or substitute the primary dataset now

This Week's Work - Run the domain-classifier shift diagnostic: train a logistic regression on frozen VLM features to predict site of origin; record its AUC. - Download and standardise the secondary dataset into the unified schema. - Freeze all splits; write the manifest; content-hash it. - Decide the achievable ε range from n_pos, using the 10/ε rule. - Read Angelopoulos et al., "Conformal Risk Control" (ICLR 2024), carefully. Weekly Deliverable Secondary dataset in hand; split manifest hashed and committed. Gate Review / Evidence (Milestone) - Logbook entry with the domain-classifier AUC and what it implies (real shift / weak shift / no shift). - If the Week-2 hard gate condition is not met, the pivot decision recorded explicitly, not deferred.

WEEK 3 — The Quantile, Tested First

This Week's Work - Implement conformal/quantile.py with the corrected ⌈(n+1)(1−α)⌉/n level. - Write tests/test_validity.py: 500 trials on synthetic exchangeable data, asserting empirical coverage within tolerance of nominal; wire into CI. - Implement split CP with LAC. - Begin gold labelling — 60 images. Weekly Deliverable CI runs the validity test on every push; 60 gold labels complete. Review Evidence / Logbook Entry CI badge green on the repository; gold-label count logged.

WEEK 4 — Baselines and Scores S1–S2

This Week's Work - Implement APS and RAPS. - Build the score registry; implement S1 (classifier logit) and S2 (generative log-probability). - Precompute and cache all scores into the scores table. - Gold labelling — 70 more images (130 total). Weekly Deliverable Three conformal-prediction variants running; score cache populated. Review Evidence / Logbook Entry 130 gold labels logged; sample cached scores shown on request.

WEEK 5 — Validity on Real Data MILESTONE / GATE — Figure F2 must land on the nominal diagonal within ±2 points — halt and debug otherwise

This Week's Work - Implement the 100-seed evaluation harness (eval/protocol.py). - Run E1 on the exchangeable split and produce Figure F2. - Implement non-conformal baselines B1–B3. - Gold labelling — 70 more images (200 total). Weekly Deliverable Figure F2 exists and coverage lands on the nominal line within ±2 points. Gate Review / Evidence (Milestone) - Figure F2 shown at review, with the ±2-point tolerance visibly satisfied. - If F2 misses the diagonal: the specific one of the four usual causes (off-by-one, sign error, split leakage, calibration-set fitting) identified and fixed before proceeding — logged either way.

WEEK 6 — Conformal Risk Control

This Week's Work - Implement crc.py with the monotone miss-rate loss. - Unit-test monotonicity of L(λ) explicitly. - Implement S3 (verbalized confidence) and S4 (detector objectness). - Run CRC at ε ∈ {0.10, 0.05, 0.02, 0.01}. - Finish gold labelling — 100 more images (300 total, complete). Weekly Deliverable CRC produces valid λ̂ at all four risk levels; 300 gold labels complete. Review Evidence / Logbook Entry CRC output table across the four ε values; gold-labelling milestone confirmed complete.

WEEK 7 — Learn-then-Test & Label Noise

This Week's Work - Implement ltt.py: Hoeffding–Bentkus p-values, fixed-sequence FWER control. - Compare CRC against LTT and quantify the efficiency cost of the PAC guarantee. - Run the label-noise analysis: κ between GPT-4V and gold labels, plus the guarantee-degradation experiment. Weekly Deliverable LTT working; label-noise section drafted. Review Evidence / Logbook Entry κ value reported, with the guarantee-degradation number stated plainly in the logbook.

WEEK 8 — Score Comparison MILESTONE / GATE — Gate 1 — Figure F3 exists, Method and Setup sections written, half the paper is real

This Week's Work - Implement S5 (MC-dropout), S6 (feature typicality), S7 (learned combination, fitted strictly on the tuning split). - Run E2 across all seven scores, 100 seeds. - Produce Figure F3. - Write §Method and §Setup of the paper — roughly three pages. Weekly Deliverable Figure F3 complete; Method and Setup sections drafted. Gate Review / Evidence (Milestone) Figure F3 reviewed; the drafted paper sections read aloud or shared for a sanity check.

WEEK 9 — Efficiency Curve

This Week's Work - Implement triage/policy.py and triage/economics.py. - Compute human-review fraction across the ε sweep for the best three scores. - Begin Figure F4. - Run the synthetic-corruption shift probe as a controlled second axis. Weekly Deliverable HRF pipeline complete; Figure F4 in draft. Review Evidence / Logbook Entry Draft F4 shown, even if not yet publication-ready.

WEEK 10 — F4 Final & LOSO Harness MILESTONE / GATE — Figure F4 (the paper’s centrepiece) publication-ready; first evidence of the shift failure

This Week's Work - Finish Figure F4 with bootstrap confidence intervals. - Build the leave-one-site-out fold generator. - Run the first LOSO pass with vanilla split CP. - Record the coverage gap per held-out site. Weekly Deliverable Figure F4 publication-ready; first LOSO coverage-gap numbers in hand. Gate Review / Evidence (Milestone) Publication-ready F4 reviewed; the per-site coverage gap table shown, however it turns out.

WEEK 11 — Shift Corrections

This Week's Work - Implement mondrian.py (group-conditional CP). - Implement weighted.py — domain classifier over VLM features, likelihood-ratio weights, effective-sample-size diagnostics. - Run both under the LOSO protocol. Weekly Deliverable Two shift-correction methods evaluated under LOSO. Review Evidence / Logbook Entry Recovered-coverage numbers for both methods logged side by side with the uncorrected gap.

WEEK 12 — Localized CP & Pivot Check MILESTONE / GATE — Gate — decide whether the shift contribution is real, or pivot the paper’s framing per the pre-registered plan

This Week's Work - Implement localized.py with the latent-similarity weighting and its nonlinear transform. - Complete the LOSO comparison across all four methods. - Produce Figure F5. - Make the honest Week-12 assessment: is the LOSO coverage gap under 2 points (no real shift), or is it a genuine, reportable finding? Weekly Deliverable Figure F5 complete; a written decision on the paper’s framing for Part 3. Gate Review / Evidence (Milestone) The pivot decision recorded explicitly in the logbook — including the case where the honest answer is a null result.

WEEK 13 — Recovery Analysis & Conditional Coverage

This Week's Work - Produce Figure F6 — recovered coverage against efficiency cost, all four methods. - Produce Figure F7 — class-conditional coverage heatmap. - Compute size-stratified coverage violation (SSCV) for every method. - Write §Results — roughly two pages. Weekly Deliverable F6 and F7 complete; Results section drafted. Review Evidence / Logbook Entry Both figures reviewed together with the drafted Results text.

WEEK 14 — Service, Console, Closing Figures

This Week's Work - Build the FastAPI service per the service contract; measure latency. - Build the one-screen console (Streamlit is an acceptable substitute for React). - Produce Figures F1, F8, F9. - Write §Discussion and §Limitations. Weekly Deliverable Working demo; all nine figures complete; full paper draft. Review Evidence / Logbook Entry Live demo of the console and the p95 latency number; full draft assembled for the first time.

WEEK 15 — Write, Cut, Rewrite

This Week's Work - Complete §Intro, §Related Work, §Abstract — abstract written last. - Full editing pass: cut 20% of the words. - Verify every number in the text against its source figure, every one. - Ask a faculty member and one strong peer to read the draft. Weekly Deliverable Complete draft, internally reviewed. Review Evidence / Logbook Entry Reviewer feedback logged, even if only partially addressed yet.

WEEK 16 — Ship It MILESTONE / GATE — Gate 2 — arXiv preprint public with a permanent identifier

This Week's Work - Address reviewer feedback. - Run the reproducibility check: clone into a fresh container, run make figures, confirm every figure regenerates. - Release the calibration benchmark and mint a Zenodo DOI. - Post to arXiv (cs.CV, cross-list stat.ML). - Update the repo README with the arXiv link and the headline results table. Weekly Deliverable arXiv preprint public and permanently linkable. Gate Review / Evidence (Milestone) arXiv identifier shown live; fresh-clone reproduction confirmed successful.

WEEK 17 — Amplify

This Week's Work - Record the 90-second demo video. - Write the long-form technical blog post. - Polish the repository README to publication standard. - Email the authors of the two closest related papers with one specific, well-posed question each. Weekly Deliverable Video, blog post, polished repo, and two emails sent. Review Evidence / Logbook Entry Video link and blog post shown; the two emails logged (sent, not necessarily answered yet).

WEEK 18 — Convert MILESTONE / GATE — Project closed — applications carry the preprint link

This Week's Work - Submit to a workshop against a currently-open CFP. - Fold the SOP paragraph and CV bullets into the TU Delft, TUM, and ETH applications. - Write the interview talking points onto a single index card and rehearse them aloud. - Archive everything; write the closing retrospective. Weekly Deliverable Applications submitted, each carrying the preprint link; project formally closed. Gate Review / Evidence (Milestone) Final retrospective entry in the logbook, summarising what shipped against the original 8-point definition of done.

# Git & GitHub Practices

Solo execution removes the need for a branching strategy — commit directly to main, in small, coherent, frequent commits. Conventional-commit prefixes replace code review as the discipline that keeps history legible.

| Prefix | Used For | Example |
| --- | --- | --- |
| feat | New functionality (a conformal method, a pipeline stage, the console) | feat: implement conformal risk control (crc.py) |
| fix | Bug fixes | fix: correct off-by-one in split-CP quantile |
| exp | Experiment runs and figure generation | exp: run E2 score comparison, 100 seeds |
| paper | Paper writing and figure integration | paper: draft §Method, add Figure F3 |
| data | Dataset, labelling, or split-manifest changes | data: freeze train/cal/test split manifest |
| docs | README, architecture notes, this work plan | docs: update README with arXiv link |

Every week should end with at least one commit and one logbook line, even in a slow week — three consecutive days without a commit is the pre-registered early-warning signal for solo motivation drop.

# Milestone / Gate Summary

| Milestone | Week | What It Confirms |
| --- | --- | --- |
| Gate — data & shift viability | 2 | At least 400 defect-positive images across 3+ distinguishable sites, or the pivot to a substitute dataset is made now. |
| Gate — validity (F2) | 5 | Empirical coverage lands on the nominal diagonal within ±2 points before any shift work begins. |
| Gate 1 — scores (F3) | 8 | The nonconformity-score comparison is complete; half the paper is real. |
| Centrepiece — efficiency curve (F4) | 10 | The paper’s central figure is publication-ready, with the first LOSO evidence in hand. |
| Gate — shift pivot check | 12 | An honest decision on whether the shift contribution is real, made against the pre-registered criterion, not under pressure later. |
| Gate 2 — arXiv live | 16 | The preprint is public with a permanent identifier — the artefact every December application links to. |